## QA Summary
| Project Name: | KULINARYA | Test Modules Created by: | Jahzel
| Test Environment | Test Environment Here | Test Executed by: | Jahzel
QA SUMMARY REPORT
PASSED |  | FAILED |  | PENDING
67 |  | 5 |  | 5
MODULE REF CODE | MODULE CONTENT | NO. OF TEST CASES | PASSED | FAILED | PENDING
Module1A | Log in Page | 10 | 9 | 0 | 1
Module 2A | Sign up Page | 13 | 12 | 0 | 1
Module 3A | Landing Page | 7 | 4 | 1 | 2
Module 4A | Page Header | 9 | 8 | 1 | 0
Module 5A | Recipe Page | 18 | 14 | 3 | 1
Module6A | Create Recipe Page | 20 | 20 | 0 | 0
Total test cases |  | 77 | 67 | 5 | 5 | 77
Percentage |  |  | 87.01% | 6.494% | 6.494% | 100%

## Module1A
| Project Name: | KULINARYA | Test Modules Created by: | Jahzel | QA STATUS
[5 empty] | PASSED | FAILED | PENDING
| Module Name: | Log-In Page | Test Executed by: | Jahzel | 9 | 0 | 1
PRE-CONDITION |  |  | DEPENDENCIES |  | TEST PRIORITY
Test Case# | Function | Test Title | Status | Notes/Related Issues
TCM1A-0001 | Negative Testing in Login form | Insert an unregistered input in the "Email Address" field | PASSED
TCM1A-0002 |  | Insert a wrong input in the "Password" field | PASSED
TCM1A-0003 |  | Blank "Email" field | PASSED
TCM1A-0004 |  | Blank "Password" field | PASSED
TCM1A-0005 | Positive Testing in Log-in form | Complying all the needed valid inputs in the "Login" page | PASSED
TCM1A-0006 | Login using Google | Login using Gmail | PASSED
TCM1A-0008 | Forgot Password | "Forgot Password" link | PENDING | PAGE NOT FOUND
TCM1A-0009 | Sign up Button | Sign up Button | PASSED
TCM1A-0010 | Sidebar button funtionality | Sidebar button | PASSED | yung arrow button
TCM1A-0011 | Home button functionality on sidebar. | Home button | PASSED | yung logo
TCM1A-0012 | Hide password | Password privacy | PASSED

## Module2A
| Project Name: | KULINARYA | Test Modules Created by: | Jahzel | QA STATUS
[5 empty] | PASSED | FAILED | PENDING
| Module Name: | Sign-up Page | Test Executed by: | Jahzel | 12 | 0 | 1
PRE-CONDITION |  |  | DEPENDENCIES |  | TEST PRIORITY
Test Case# | Function | Test Title | Status | Notes/Related Issues
TCM2A-00001 | Negative Testing of Sign up | Leave the first name blank | PASSED
TCM2A-00002 |  | Leave the last name blank | PASSED
TCM2A-00003 |  | Enter invalid email address | PASSED
TCM2A-00004 |  | Leave the email address blank | PASSED
TCM2A-00005 |  | Enter Invalid password | PASSED
|  | Leave the password field blank | PASSED
TCM2A-00006 |  | Enter repeat password differs from the password | PASSED
TCM2A-00007 | Sign up with email | Sign up with email | PASSED
TCM2A-00008 | Email Verification | Verify through email | PASSED
TCM2A-00009 | Log in button | Log in | PENDING | Redirecting to /home which is already removed because landing and home route already merge
TCM2A-00010 | Sidebar button funtionality | Sidebar button | PASSED | yung arrow button
TCM2A-00011 | Home button functionality on sidebar. | Home Button | PASSED | yung logo
TCM2A-00012 | Hide password | Password privacy | PASSED
TCM2A-00013

## Module3A
| Project Name: | KULINARYA | Test Modules Created by: | Jahzel | QA STATUS
[5 empty] | PASSED | FAILED | PENDING
| Module Name: | Landing page | Test Executed by: | Jahzel | 4 | 1 | 2
TEST PRIORITY
Test Case# | Function | Test Title | Actual Result | Status | Notes/Related Issues
TCM3A-00001 | Verify functionality on landing page | Landing Button | As expected | PASSED | Logo button
TCM3A-00002 | Verify functionality on landing page | Explore Now in sidebar | As expected | PASSED
TCM3A-00003 | Verify functionality on landing page | Featured recipes | As expected | PASSED
TCM3A-00004 | Verify functionality on landing page | Share Now | As expected | PASSED
TCM3A-00005 | Verify functionality on landing page | Top Recipe Sharers | hindi nag d-direct sa profile pag ni-click yung view profile | FAILED | page not found nakalagay
TCM3A-00006 | Verify functionality on landing page | Top Engaged Recipes | kapag naka-slide sa LEFT MOST part, yung left most recipe yung navi-view WHEN CLICKING THE LEFT ARROW | PENDING | wrong page ba 'to? or no naman?
TCM3A-00007 | Verify functionality on landing page | Top Engaged Recipes | kapag naka-slide sa RIGHT MOST part, WHEN CLICKING THE RIGHT ARROW, no page found | PENDING | PAGE NOT FOUND
TCM3A-00008
TCM3A-00009
TCM3A-00010
TCM3A-00011
TCM3A-00012
TCM3A-00014
TCM3A-00015
TCM3A-00016
TCM3A-00017
TCM3A-00018
TCM3A-00019
TCM3A-00016
TCM3A-00017
TCM3A-00018
TCM3A-00019
TCM3A-00020
TCM3A-00021
TCM3A-00022

## Module4A
| Project Name: | KULINARYA | Test Modules Created by: | Jahzel | QA STATUS
[5 empty] | PASSED | FAILED | PENDING
| Module Name: | Page Header | Test Executed by: | Jahzel | 8 | 1 | 0
PRE-CONDITION |  |  | DEPENDENCIES |  |  | TEST PRIORITY
Test Case# | Function | Test Title | Expected Result | Actual Result | Status | Notes/Related Issues
TCM4A-00001 | Verify landing page button functionality | Landing page button | The Landing page should appear when the landing page button is clicked. | As expected | PASSED
TCM4A-00002 | Verify Home button Functionality | Home button | The Home page should appear when the home button is clicked. | As expected | PASSED
TCM4A-00003 | Verify Recipes button Functionality | Recipes button | The Recipes page should appear when the recipes button is clicked. | As expected | PASSED
TCM4A-00004 | Verify Notification button Functionality | Notification Button | The pop up Notifications should appear when the notification button is clicked. | As expected | PASSED
TCM4A-00005 | Verify User Account button Functionality | User Account | The profile, settings, logout and toggle theme button should appear. | As expected | PASSED
TCM4A-00006 | Verify Profile button Functionality | Profile | The User profile will appear. | As expected | PASSED
TCM4A-00007 | Verify Settings button Functionality | Settings | The Settings should appear. | Page Not found | FAILED
TCM4A-00008 | Verify Logout button functionality | Logout | User Account will logout | As expected | PASSED
TCM4A-00009 | Verify Toggle theme functionality | Toggle Theme | The Page will become light or dark | As expected | PASSED
TCM4A-00010
TCM4A-00011
TCM4A-00012
TCM4A-00013

## Module5A
| Project Name: | KULINARYA | Test Modules Created by: | Jahzel | QA STATUS
[5 empty] | PASSED | FAILED | PENDING
| Module Name: | Recipe Page | Test Executed by: | Jahzel | 14 | 3 | 1
PRE-CONDITION |  |  | DEPENDENCIES |  |  | TEST PRIORITY
Test Case# | Function | Test Title | Expected Result | Actual Result | Status | Notes/Related Issues
TCM5A-0001 | Verify functionality on recipe page | Recipe Navigation Button | The Recipe page will appear when recipe button is clicked | As expected | PASSED
TCM5A-0002 | Verify recipe post display | Recipe Post Display | All approved recipes will appear | As expected | PASSED
TCM5A-0003 | Creating Recipes (user) | Create button (user) | Recipe Create page should appear | As expected | PASSED
TCM5A-0004 | Creating Recipes (guest) | Create button (guest) | Create button should not appear when not registered or a guest only | As expected | PASSED
TCM5A-0005 | Recipe Display | Recipe Display Viewing | When clicked the recipe post it will redirect to the recipe viewing page | Page Not Found | FAILED | 404
TCM5A-0006 |  | Recipe Display User Own Recipe Post | When a recipe is posted by the user, the recipe display card will show a three-dot menu that, when clicked, displays Edit and Delete options | As expected | PASSED
TCM5A-0007 |  | Recipe Display User Own Recipe Post (Edit Button) | When clicked it will go to edit recipe page | As expected | PASSED
TCM5A-0008 |  | Recipe Display User Own Recipe Post (Delete Button) | When clicked the recipe post will be deleted | Coming Soon (Toast) | PENDING
TCM5A-0009 | Recipe Filters (Positive Testing) | Origin Filter | When an origin province is selected, the recipe display should only show recipes from the selected province | As expected | PASSED
TCM5A-0010 |  | Category Filter | When a category is selected, the recipe display should only show recipes from the selected category | As expected | PASSED
TCM5A-0011 |  | Search | Show specific searched recipe | As expected | PASSED
TCM5A-0012 |  | Page Limit | Display Recipes based on the page limit | As expected | PASSED
TCM5A-0013 |  | Newest to Oldest Filter | Display newest posted recipes to oldest. Vice Versa | As expected | PASSED
TCM5A-0014 |  | Previous Page Button | Proceed to previous page when in page 2 and so on | As expected | PASSED
TCM5A-0015 |  | Previous Page Button | When in Page 1, previous page can't be clicked. also it should be grayed out. no color when hover | Previous page button when hover have color orange and can be click but not directing to other page | FAILED
TCM5A-0016 |  | Next Page Button | Proceed to the next page | As expected | PASSED
TCM5A-0017 |  | Reset Button | Reset all selected filters | As expected | PASSED
TCM5A-0018 | Recipe Filters (Negative Testing) | Next Page Button | When in last page the next button can't be clicked and grayed out. When clicked it should not be reddirecting to a next page or other page | Next page button can be still clicked and proceeding to other page but showing no recipes found | FAILED

## Module6A
| Project Name: | KULINARYA | Test Modules Created by: | Jahzel | QA STATUS
[5 empty] | PASSED | FAILED | PENDING
| Module Name: | Create Recipe Page | Test Executed by: | Jahzel | 20 | 0 | 0
PRE-CONDITION |  |  | DEPENDENCIES |  |  | TEST PRIORITY
Test Case# | Function | Test Title | Actual Result | Status | Notes/Related Issues
TCM5A-0001 | Creating Recipes Step 1 (Negative Testing) | Step 1 (Leave all fields blank) | Should not proceed to next page. Show error validations | As expected | PASSED
TCM5A-0002 |  | Step 1 (Leave province and category blank) | Should not proceed to next page. Show error validations | As expected | PASSED
TCM5A-0003 |  | Step 1 (Leave category blank) | Should not proceed to next page. Show error validations | As expected | PASSED
TCM5A-0004 | Creating Recipes Step 1 (Positive Testing) | Step 1 (Put all neccessary details in title, province and category) | Proceed to the next page or step 2 | As expected | PASSED
TCM5A-0005 | Creating Recipes Step 2 (Negative Testing) | Step 2 (Leave all fields blank) | Should not proceed to next page. Show error validations | As expected | PASSED
TCM5A-0006 |  | Step 2 (Leave ingredient blank) | Should not proceed to next page. Show error validations | As expected | PASSED
TCM5A-0007 |  | Step 2 (Leave procedure blank) | Should not proceed to next page. Show error validations | As expected | PASSED
TCM5A-0008 |  | Step 2 Ingredients. Add Button then leave blank | Should not proceed to next page. Show error validations | As expected | PASSED
TCM5A-0009 |  | Step 2 Procedure. Add Button then leave blank | Should not proceed to next page. Show error validations | As expected | PASSED
TCM5A-0010 | Creating Recipes Step 2 (Positive Testing) | Step 2 (Put all neccessary details in ingredient and procedure) | Proceed to the next page or step 3 | As expected | PASSED
TCM5A-0011 |  | Step 2 Previous Button | Proceed to the previous page | As expected | PASSED
TCM5A-0012 |  | Step 2 Delete Button | Delete Added Ingredient or Procedure | As expected | PASSED
TCM5A-0013 | Creating Recipes Step 3 (Negative Testing) | Step 3 (Leave all fields blank) | Should not proceed to next page. Show error validations | As expected | PASSED
TCM5A-0014 | Creating Recipes Step 3 (Positive Testing) | Step 3 (Upload Main Picture of Recipe) | Proceed to the next page or step 4 | As expected | PASSED
TCM5A-0015 |  | Step 3 Remove Button | Uploaded Picture or Video will be removed | As expected | PASSED
TCM5A-0016 |  | Step 3 Change Button | Uploaded Picture or Video will be changed | As expected | PASSED
TCM5A-0017 |  | Step 3 Previous Button | Proceed to the previous page | As expected | PASSED
TCM5A-0018 | Creating Recipes Step 4 (Positive Testing) | Step 4 Preview details inputted | All details inputted will show from title to picture/video | As expected | PASSED
TCM5A-0019 |  | Step 4 Submit Button | Succesful creating post recipe. Will show a successful message and to wait for moderation | As expected | PASSED
TCM5A-0020 |  | Step 4 Previous Button | Proceed to the previous page | As expected | PASSED